## GOALS & OBJECTIVES
Goal 1: Leadership & Strategy - Promote leadership, education and empowerment both in government, and public and private sectors to foster the implementation of resiliency strategies across disciplines and communities.
LS1: Incorporate resiliency into local and regional plans, policies and objectives.
LS2: Plan fiscally to implement resilient and sustainable solutions to long-term impacts.
LS3: Implement strategies to promote adaptive measures that keep people and property safe from natural hazards.
LS4: Engage and educate private sector stakeholders, elected officials and other members of the community about strategies to increase resilience in the built, natural, and social environment
Goal 2: Economic & Society - Provide opportunities and strategies to foster economic prosperity and improve social equity and justice in preparation for and recovery from stressors and shocks.
ES1: Protect high-value assets from natural hazards.
ES2: Educate business about access to funding and financing services related to resiliency and sustainability.
ES3: Facilitate and support the efficient recovery of business operations after an event.
ES4: Increase skilled labor force.
ES5: Improve social equity and justice in decision making process.
Goal 3: Infrastructure & Environment - Encourage development of cross-disciplinary plans, policies and strategies to protect the health, safety and economic welfare of residents, businesses and visitors through recognition that natural disasters, changes to climate, and human manipulation require careful consideration of when and how to develop infrastructure, natural resources and a built environment that can withstand and adapt to these changes.
IE1: Prioritize the use of Green Infrastructure as a first line of defense.
IE2: Promote interconnectivity of natural lands for habitat migration.
IE3: Enhance stormwater systems to be more resilient.
IE4: Improve water quality in surface water bodies.
IE5: Incorporate resiliency into local and regional plan, policies and objectives.
IE6: Preserve and adapt the built environment to keep people safe from and mitigate current and future natural hazards.
IE7: Improve community mobility while improving vulnerable transportation infrastructure.
Goal 4: Health & Well Being - Create resilient communities by facilitating programs, opportunities, and community-wide education pertaining to local sustainability, disaster response, and climate change mitigation strategies.
HW1: Improve capacity of jurisdictions to better respond to hazard events.
HW2: Improve capacity of medical facility operations to prepare for and recover from natural disasters and future conditions.
HW3: Promote sustainable practices in government owned facilities.
HW4: Engage residents and business owners with locally relevant information about expected future changes in natural hazards and sustainable practices.
HW5: Improve access to resources for the homeless, special needs, elderly, low income, and English-limited residents.

## Leadership and Strategy
Goal | Objective | Action | Agency or Department | Task | Year | Related Plans
Leadership & Strategy | LS1: Incorporate resiliency into local and regional plans, policies and objectives. | LS1.1 | ECFRPC All Jurisdictions | Work with experts, agencies, public, stakeholders and elected officials across the region to develop the framework of a regional collaborative to focus on resilience. | 1
|  | LS1.2 | ECFRPC | Evaluate existing programs as related to regional resilience action programs and plans. | 1
|  | LS1.3 | Planning Department Sustainability Board Brevard County Sustainability Working Group | Create a jurisdiction-wide Sustainability/Resiliency Plan through the recommendations of the Sustainability Board, if applicable. | 2 | Sustainability Plan
|  | LS1.4 | ECFRPC All Jurisdictions | Formalize the framework of the regional resilience collaborative through resolution. | 2
|  | LS1.5 | All Jurisdictions | Secure a Chief Resiliency and/or Sustainability Officer to coordinate with private and public sectors. | 2
|  | LS1.6 | All Jurisdictions All Agencies | Prioritize the review of all plans, policies and procedures to assess inclusion of resilience strategies or impediments, if not already completed. | 3
|  | LS1.7 | All Jurisdictions All Agencies | Participate in a county-wide workshop to share best practices, needs and progress of local planning in regards to implementing the action plan and other resilience strategies (local level). | 4
|  | LS1.8 | ECFRPC All Jurisdictions | Reassess existing framework and goals of the regional resilience collaborative. | 5
|  | LS1.9 | All Jurisdictions | Reassess indicators established in the local Sustainability/Resiliency Plan. | 5
Leadership & Strategy | LS2: Plan fiscally to implement resilient and sustainable solutions to long-term impacts. | LS2.1 | All Local Government Commission All Jurisdictional Departments Public | Assess CIP to ensure inclusion of sustainable and resilient projects. | 1 | Capital Improvement Plan/Element
|  | LS2.2 | Public Works Department All Local Government Commission | Procure funding and staff/contractor to update all stormwater system facilities in a master GIS database. | 1
|  | LS2.3 | Local Government Commission Jurisdictional Departments Public Natural Resources Department Watershed Management Program | Conduct budgeting workshops and surveys to determine appropriate ways to build reserves and adjust budgets to include specific line items to be proactive in creating and maintaining sustainable and resilient communities. | 2
|  | LS2.4 | All Local Government Commission All Jurisdictional Departments Public | Conduct survey of stakeholders to assess priority and funding of conservation lands and green infrastructure. | 3
|  | LS2.5 | All Local Government Commission | Investigate and develop innovative long-term funding and revenue generators. | 4
|  | LS2.6 | All Local Government Commission | Implement reserve building strategies incrementally to be proactive in creating sustainable and resilient communities. | 4
|  | LS2.7 | All Local Government Commission All Jurisdictional Departments | Reassess budgeting and CIP involving resilient and sustainable projects to ensure continuing inclusion. | 5 | Capital Improvement Plan/Element
|  | LS2.8 | SJRWMD Natural Lands Programs Natural Resource Department FDEP 1000 Friends of Florida NGOs | Evaluate strategies and alternative analysis for longer term funding for acquisition / management program. | 5
Leadership & Strategy | LS3: Implement strategies to promote adaptive measures that keep people and property safe from natural hazards. | LS3.1 | Natural Resources Department Planning Department SJRWMD UF IFAS Extension Natural Resources Conservation Service (USDA) | Assess and update LDC as necessary to allow private land owners to implement native vegetation programs, or other efforts that allow water to be treated on site. | 1
|  | LS3.2 | Planning Department | Research appropriate parking standards for the community, and identify parking lots that can potentially be downsized to include green infrastructure and permeable surfaces as well as strategies to mitigate the heat island effect. | 1
|  | LS3.3 | Natural Resources Department Planning Department | Streamline the permit process in order to allow private land owners to implement native vegetation programs, or other efforts that allow water to be treated on site. | 2 | Department Permitting Handbook
|  | LS3.4 | Sustainability Boards All Jurisdictions ECFRPC | Ensure passing of information and infographic templates to and from agencies and jurisdictions through websites to better relay information. | 2
|  | LS3.5 | Planning Department | Update parking standards within Land Development Regulations to allow for additional space to include green infrastructure, permeable surfaces and other strategies that mitigate the heat island effect. | 2 | Land Development Regulations
|  | LS3.6 | Planning Department Public Works Department | Prioritize public and private parking lots that can be retrofitted to include more permeable surface to reduce stormwater loads and treat water on-site. | 3
|  | LS3.7 | Utilities Department Emergency Management Public Works Department | Add stormwater mitigation efforts in parking lots to the stormwater management plan, LDRs, CIE where necessary and find best areas for retrofitting opportunities. | 4 | Stormwater Management Plan Comprehensive Plan Land Development Regulations
|  | LS3.8 | Utilities Department Public Works Department | Reassess improvements to stormwater run off and quality in areas of new projects. | 5
Leadership & Strategy | LS4: Engage and educate private sector stakeholders, elected officials and other members of the community about strategies to increase resilience in the built, natural, and social environment. | LS4.1 | ECFRPC All Jurisdictions | Find champions and strong advocates both elected and non-elected to participate in the regional resilience collaborative and locally. | ongoing
|  | LS4.2 | All Local Government Commission All Jurisdictional Departments ECFRPC Florida Sea Grant | Conduct new leadership orientation. | ongoing
|  | LS4.3 | ECFRPC | Create a regional education plan/tool box for use across the region for all levels and sectors both private and public as well as citizens. | 1
|  | LS4.4 | Sustainability Board Planning Department Economic Development Commission UF IFAS Extension | Hold workshops or one-on-one meetings with private sector stakeholders to educate and train them on sustainable practices. | 1
|  | LS4.5 | All Local Government Commission | Assess applicability of a Sustainability Board and develop goals for the board with a diverse group of stakeholders. | 1
|  | LS4.6 | Sustainability Board | Create a social media account for the Sustainability Board. | 1
|  | LS4.7 | Sustainability Board Planning Department UF IFAS Extension | Develop sustainability trainings for elected officials, boards, and staff that includes information on hazard mitigation and sustainability principles. | 1 | Sustainability Plan
|  | LS4.8 | Sustainability Board Planning Department Economic Development Commission UF IFAS Extension | Hold workshops or one-on-one meetings with elected officials to inform them on sustainable practices. | 1
|  | LS4.9 | Natural Resource Department UF IFAS Extension | Create workshops and info graphics to educate the public and elected officials about economic and mitigation benefits of ecosystem services. | 2
|  | LS4.10 | RAPP Steering Committee ECFRPC | Host a Regional Climate Summit. | 2
|  | LS4.11 | Sustainability Board Planning Department Economic Dev't Commission Natural Resource Department UF IFAS Extension | Develop an educational outreach plan with all appropriate departments to ensure stakeholders and elected officials are continuously engaged and educated about resilience at important junctures. | 3/ on-going
|  | LS4.12 | Natural Resource Departments Sustainability Boards UF IFAS Extension | Conduct the series of natural resource workshops for the public and elected officials to educate them about economic and mitigation benefits of conservation lands etc. | 3
|  | LS4.13 | Planning Department Sustainability Board RRAP Steering Committee ECFRPC UF IFAS Extension Regional Stakeholders | Provide outreach and educational opportunities to residents to learn about the importance of developing away from the natural hazard zones. | 3
|  | LS4.14 | Sustainability Board Planning Department UF IFAS Extension | Develop volunteer initiatives based off of the educational opportunities in order to continue learning through hands-on activity. | 4
|  | LS4.15 | Sustainability Board Planning Department Economic Dev't Commission Natural Resource Department UF IFAS Extension | Re-evaluate workshops and educational materials to determine gaps and lessons learned. | 4
|  | LS4.16 | Sustainability Board Planning Department Economic Development Commission UF IFAS Extension Natural Resource Department | Using findings from LS4.15, update educational outreach plan, programs and materials. | 5
|  | LS4.17 | Sustainability Board UF IFAS Extension Planning Department | Reassess engagement techniques and areas that would benefit from more participation/education of the community. | 5

## Health and Wellbeing
Goal | Objective | Action | Agency | Task | Year | Related Plans
Health & Well Being | HW1: Improve capacity of jurisdictions to better respond to hazard events. | HW1.1 | Emergency Management Votran SCAT | Update evacuation plans to represent newest data of areas that are transportation dependent that will need assistance in evacuation and re-entry. | on-going | Evacuation Plans Special Needs Registry
|  | HW1.2 | Emergency Management Votran SCAT | Identify/update, within the countywide COOP and transit plans, a listing of priority transit routes for operation after a natural hazard event - as needed. | on- going | County Post-Disaster Recovery Plans CEMP Annex
|  | HW1.3 | Emergency Management | Identify staging areas for fueling trucks pre and post disaster for efficient evacuation and re-entry. | on- going | County COOP Plans
|  | HW1.4 | Public Works Department Emergency Management Planning Department | Assess potable water supplies and infrastructure from natural disaster impacts such as sewage infiltration. | on- going
|  | HW1.5 | Emergency Management All Jurisdictional Departments | Update plans to include information gathered from Hurricane Irma After Action Reports. | 1
|  | HW1.6 | Emergency Management | Identify and prioritize critical facilities, including storm/wastewater, waste management, transportation, etc. with generator needs and add to the appropriate funding list (i.e. LMS, CIP, etc.). | 1 | LMS CEMP COOP
|  | HW1.7 | Public Works Department Emergency Management CERT | Investigate the feasibility of and needs associated with alternative energy fleet vehicles for emergency response use. | 2 | County COOP Plans Capital Improvement Plan/Element
|  | HW1.8 | Emergency Management USDA Florida Department of Agriculture | Work with ranchers and farmers to determine gaps and needs associated with livestock and farming preparedness and recovery, especially, excessive long-term flooding. | 2
|  | HW1.9 | ECFRPC Economic Development Commission Chambers of Commerce | Assess economic development plans, CRA plans, etc. for diversification and identify adaptive measures to economic vulnerabilities. (CDBG) | 3
|  | HW1.10 | Emergency Management Department of Health United Way IFAS DACS Food Pantries Faith Based Organizations | Assess food insecurity in vulnerable populations to prepare for hazard events. | 3
|  | HW1.11 | Emergency Management ECFRPC | Develop/Re-convene long-term care working group with the goal to create a county-wide model for preparedness and recovery and coordinate and determine an agency responsible. | 4
|  | HW1.12 | Emergency Management | Identify funding to secure generators for facilities identified in HW1.7. | 4 | LMS CEMP COOP
|  | HW1.13 | Emergency Management Department of Health United Way IFAS DACS Food Pantries Faith Based Organizations | Work with food pantries and other resources to close the gaps identified in analysis HW1.10. | 4
|  | HW1.14 | Public Works Department Emergency Management Planning Department | Reassess gaps in response to hazard events and address those gaps in future plans. | 5
Goal | Objective | Action | Agency | Task | Year | Related Plans
Health & Well Being | HW2: Improve capacity of medical facility operations to prepare for and recover from natural disasters and future conditions. | HW2.1 | Emergency Management Medical Facilities | Hold training workshops at medical facilities that test response and evacuations from a hazard event. | on- going | Facility COOP plans Facility Evacuation/Response Plans
|  | HW2.2 | Emergency Management Planning Department Medical Facilities | Assess vulnerability to medical facilities (hospitals, hospices, dialysis centers, assisted living facilities, nursing homes, etc.), helicopter pads and access points from sea level rise, flooding and storm surge impacts. | 1 | TPO and Local Vulnerability Analyses
|  | HW2.3 | Emergency Management Medical Facilities | Develop or update plans for natural disasters such as strong hurricanes and tornadoes. | 2 | Facility COOP plans Facility Evacuation/Response Plans
|  | HW2.4 | Emergency Management Medical Facilities | Provide county and City emergency management with current response and evacuation plans (and as updated). | 3
|  | HW2.5 | Planning Department Medical Facilities | Determine mitigation/adaptation strategies for identified vulnerabilities to medical facilities and develop implementation plan. | 3
|  | HW2.6 | Planning Department Building/Zoning Department Sustainability Board | Assess and update future land use and zoning codes to limit or mitigate the placement of medical facilities in vulnerable areas. | 4
|  | HW2.7 | Emergency Management Medical Facilities | Reassess/update COOP and other plans with findings from the workshop in Action HW2.1 | 5 | Facility COOP plans Facility Evacuation/Response Plans
Health & Well Being | HW3: Promote sustainable practices in government owned facilities. | HW3.1 | Planning Department | Reassess budgets to determine for proactive resiliency and sustainability funding. | on- going
|  | HW3.2 | Planning Department | Assess feasibility of a sustainability program within the City and audit existing programs in other Cities as well as incentive programs such as Florida Green Building Coalition and the LEED program. | 1
|  | HW3.3 | Planning Department | Develop priorities, actions and goals in a local government section of a Sustainability Plan to include a focus on government owned facilities. (where applicable) | 2
|  | HW3.4 | Planning Department | Identify locations for electric charging stations, especially near/at publicly-owned properties and high employment areas. | 2
|  | HW3.5 | Planning Department | Update local codes and policies to promote sustainable and Low Impact Development practices for government owned facilities. | 3 | Comprehensive Plans Land Development Codes
|  | HW3.6 | Planning Department Building/Zoning Department Sustainability Board | Develop programs to install community gardens and green roofs on public buildings and on buildings within the community (where applicable). | 3 | Sustainability Plan
|  | HW3.7 | GIS Department Sustainability Board | Conduct energy audit within jurisdiction and develop strategies to mitigate the effects. | 3 | Sustainability Plan
|  | HW3.8 | School Board Planning Department | Work with the school board to maximize the use of green building techniques and sustainable practices to support the local government Sustainability Plan and to provide hazard mitigation opportunities. | 3 | Sustainability Plan
|  | HW3.9 | Planning Department Building/Zoning Department Sustainability Board | Assess and update future land use and zoning codes to limit or mitigate the placement of government buildings in vulnerable areas, including areas projected to be significant impacted by sea level rise by 2100. | 4
|  | HW3.10 | Planning Department Building/Zoning Department Sustainability Board | Reassess sustainability plan and metrics associated with the implementation of sustainable building practices in government facilities. | 5
Health and Wellbeing | HW4: Engage residents and business owners with locally relevant information about expected future changes in natural hazards and sustainable practices. | HW4.1 | Emergency Management All Jurisdictions | Develop and implement campaign to include in hurricane preparedness season to communicate dangers of do-it-yourself tasks and home generators with residents. | on-going | CEMP
|  | HW4.2 | Planning Department Building Department Sustainability Board | Evaluate existing programs in other jurisdications and agencies aimed at educating residents and business owners about imminent natural hazards and sustainable practices, such as the City of Orlando Greenworks, FGBC, PACE. | on- going | Sustainability Plan
|  | HW4.3 | Sustainability Boards IFAS Non-profits | Work with volunteers like religious institutions, clubs, schools etc. for beach clean-up, tree planting, bioswale creation, urban farming and other hands-on events. | ongoing
|  | HW4.4 | FEMA Sustainability Boards Emergency Management | Conduct in-depth community outreach events outside of the storm season to identify needs and barriers associated with resource accessibility and disaster response. | on- going | CEMP
|  | HW4.5 | Planning Department Building Department Sustainability Programs Public Schools PIO's PIN Joint Info Center | Create a working group of staff and sustainability board to collaborate on the best approach for educating residents and business owners about imminent natural hazards, sustainable practices, and the heat island effect. | 1 | Sustainability Plan
|  | HW4.6 | Planning Department Building Department Sustainability Board Chambers of Commerce | Develop a "Resilient Homes" program or encourage participation in an existing program based on findings from program evaluation in HW4.2. | 2 | Sustainability Plan
|  | HW4.7 | Emergency Management | Education about early warning systems that inform residents via reverse-911 and social media outlets of high tide or coastal flooding events. | 2 | County COOP Plan
|  | HW4.8 | Health Departments | Engage in public outreach related to the heat island effect and the risks associated with heat exhaustion and increased local temperatures. | 2
|  | HW4.9 | Planning Department Building/Zoning Department Sustainability Board | Develop indicators and begin tracking data to develop a baseline for future assessments. | 3 | Sustainability Plan
|  | HW4.10 | Planning Department Building Department Sustainability Board Chambers of Commerce | Develop or utilize existing incentives to increase the energy efficiency and resilience of homes and businesses. | 3 | Sustainability Plan
|  | HW4.11 | Planning Departments Sustainability Board | Educate and engage community in improving tree canopy through plantings on residential properties as well as events (Florida Friendly Landscaping / Energy Efficiency). | 4 | Sustainability Plan
|  | HW4.12 | Planning Department Building Department Sustainability Board | Develop "Return on Investment" Infographic on various resilient and sustainable strategies for homeowners and businesses. | 4 | Sustainability Plan
|  | HW4.13 | Planning Department Building Department Sustainability Board | Distribute infographic via website, social, board/committees, etc. | 4 | Sustainability Plan
|  | HW4.14 | Planning Department Building/Zoning Department Sustainability Board | Reassess sustainability plan and metrics associated with the implementation of sustainable and resilient programs and incentives in the community. | 5 | Sustainability Plan
Health & Well Being | HW5: Improve access to resources for the homeless, special needs, elderly, low income, and English-limited residents. | HW5.1 | Emergency Management | Continue to provide preparedness and storm-related information/alerts for English-limited populations including spanish and creole in all formats (in compliance with Title VI and ADA guidelines). | on-going | CEMP
|  | HW5.2 | Emergency Management PIN and JINC | Continue “primary” social media account relays all disaster-related information. | on-going | CEMP
|  | HW5.3 | Emergency Management Faith based organizations Non-profits | Continue to utilize pre-registration to identify shelters for special needs and seniors within the community. | on-going
|  | HW5.4 | Emergency Management Faith based organizations Non-profits | Prioritize and utilize the Idignity Program to ensure residents have essential documents before disasters. | on-going
|  | HW5.5 | Emergency Management Faith based organizations | Conduct in-depth community outreach events outside of the storm season to identify needs and barriers associated with resource accessibility and disaster response. | on-going
|  | HW5.6 | Emergency Management | Reassess marketing and registration process for special needs registration and determine how to fill gaps and better reach the special needs community. | 1
|  | HW5.7 | Transit Agencies | Reassess transit routes and stops based on new development, resources, jobs, and transit dependent communities. | 2
|  | HW5.8 | Emergency Management | Implement improvements to the marketing and registration process for special needs registration as found in HW 5.6. | 2
|  | HW5.8 | Planning Department Housing and Human Services Zoning Department | Identify areas outside vulnerabilities to encourage/incentivize the development of affordable housing. | 2 | Comprehensive Plan
|  | HW5.9 | Planning Department Housing and Human Services | Assess plans and policies to encourage development of future affordable housing choices outside of vulnerable areas and with access to transit, jobs, and resources. | 3 | Comprehensive Plan
|  | HW5.10 | All Jurisdictional Departments | Reassess plans and procedures to determine remaining gaps and success of implemented procedures. | 5

## ECONOMY AND SOCIETY ACTIONS
Goal | Objective | Action | Agency | Task | Year | Related Plans
Economic & Society | ES1: Protect high-value assets from natural hazards. | ES1.1 | NASA Port Canaveral Patrick Air Force Base All Jurisdictions FDOT | Conduct assessment of land use and facilities to determine vulnerabilities to sea level rise, storm surge, coastal erosion and flooding. Reassess existing assessments to new RRAP sea level rise recommendations if NOAA 2017 was not included. | 1
|  | ES1.2 | Emergency Management Economic Dev't Commission Chambers of Commerce | Identify local businesses such as gas stations, food suppliers or others that provide specific services or resources vital for recovery, thus classify them as critical facilities. | 1 | Business Resiliency Action Plan County COOP Plan
|  | ES1.3 | Port Canaveral | Assess vulnerabilities and capabilities of service and access points for critical post-storm services such as fuel tanker fill stations and discernment. Find highest risk/ short term vulnerabilities for 2040. | 1
|  | ES1.4 | Port Canaveral | Model changes in future water main pressure from the potential impacts of sea level rise to ensure that fuel stations will function properly after storm events in the long term. | 2
|  | ES1.5 | NASA Port Canaveral Patrick Air Force Base All Jurisdictions FDOT | Update plans, policies, and procedures to implement the RRAP sea level rise to be included in asset development and mitigation efforts to include timeframes relevant to long-lasting, critical infrastructure. | 2
|  | ES1.6 | Economic Development Agencies | Using vulnerability analysis findings, identify vulnerable areas of economic significance. | 2
|  | ES1.7 | Planning Department | Develop and adopt policy language that prohibits the development of high value assets in vulnerable areas or if necessary, are mitigated to the greatest extent possible. | 2
|  | ES1.8 | NASA Port Canaveral Patrick Air Force Base Planning Department Emergency Management FDOT | identify strategies and policies related to resilient rebuilding in identified vulnerable areas such as how to build back better, risk informed construction standards, streamlined processes for post disaster reconstruction, debris removal / pre-identified debris management resources, and a guide regeneration. | 3
|  | ES1.9 | NASA Port Canaveral Patrick Air Force Base Planning Department FDOT | Conduct an assessment of policy language and find existing case studies that direct high value assets away from vulnerable areas and test feasibility of those policies locally. | 3
|  | ES1.10 | NASA Port Canaveral Patrick Air Force Base All Jurisdictions FDOT | Develop possible mitigation strategies of at-risk public infrastructure identified as part of the natural hazard vulnerability assessment. | 3
|  | ES1.11 | ECFRPC | Conduct a region wide workshop focused on the financial side of resilience. | 3
|  | ES1.12 | Emergency Management Economic Development Agencies Chambers of Commerce | Work with business identified in ES1.2 to determine needs and continuity plans to aid in disaster recovery efforts. | 3 | Business Resiliency Action Plan County COOP Plan
|  | ES1.13 | NASA Port Canaveral Patrick Air Force Base All Jurisdictions FDOT | Conduct a risk-based cost-benefit analysis for mitigation strategies of at-risk structures identified as part of the natural hazard vulnerability assessment. Identify the assets with the highest short-term risk for inundation. Develop a prioritization process to address mitigation/adaptation strategies for vulnerable assets. | 4
|  | ES1.14 | Economic Development Agencies | Develop a long-term financial plan for loss of or restructure of tax base in highly vulnerable areas. | 4
|  | ES1.15 | NASA Port Canaveral Patrick Air Force Base All Jurisdictions FDOT | Finalize action plan to implement adaptation/mitigation strategies of at-risk assets identified as part of the natural hazard vulnerability assessment. | 5
Economic & Society | ES2: Educate business about access to funding and financing services related to resiliency and sustainability. | ES2.1 | Sustainability Board Chambers of Commerce | Research funding and financing services for pre/post post disaster needs and sustainable practices. Determine role of jurisdiction in the implementation of financing mechanisms. | 1
|  | ES2.2 | Sustainability Board Chambers of Commerce UF IFAS Extension Florida Sea Grant | Conduct a workshop with business owners to determine needs, wants and constraints as related to implementing resilient and sustainable practices. | 1
|  | ES2.3 | Emergency Management Economic Dev't Commission Chambers of Commerce | Create/update disseminate an educational infographic for businesses with funding and financing services for pre/post- disaster needs and sustainable practices. | 2 | Business Resiliency Action Plan County COOP Plan
|  | ES2.4 | Chambers of Commerce | Determine the feasibility and functionality of a program to help impacted businesses with rent deferment. | 3
|  | ES2.5 | Sustainability Board Chambers of Commerce Brevard County Sustainability Working Group | Include in a sustainability plan actions to help community businesses implement sustainable practices. | 3
|  | ES2.6 | Sustainability Board Chambers of Commerce | Reassess efforts and programs to fill identified gaps. | 4
Economic & Society | ES3: Facilitate and support the efficient recovery of business operations after an event. | ES3.1 | Emergency Management Economic Development Commission Chambers of Commerce Port Canaveral | Develop a process for businesses to coordinate with the EOC for review and execution of Business Continuity Plans. | 1 | Business Resiliency Action Plan County COOP Plan
|  | ES3.2 | Chambers of Commerce Workforce Agencies | Research available templates for business and employee preparedness plans and create outreach proposal for businesses to update these templates. | 1
|  | ES3.3 | Economic Development Commission Tourism Development Council | Create a tourism marketing program to implement after a disaster event to bring tourists back by showcasing that the area is "Open for Business". Create PSA's and other materials. | 1
|  | ES3.4 | Economic Development commission | Identify “point person” in local government to act as a liaison between the business community and the local government for resiliency. | 1
|  | ES3.5 | Chambers of Commerce Emergency Management EOC | Develop a section on agency website focused on disaster preparedness and include links to business continuity plan and employee disaster plan templates. | 2
|  | ES3.6 | Emergency Management Chambers of Commerce Workforce Agencies | Develop "one-pager" with best practices and links for responding to and preparing for hazard events. Create/update and disseminate an educational infographic for businesses with emergency information to access for post disaster needs. | 2
|  | ES3.7 | Emergency Management Economic Development Commission Chambers of Commerce | Begin to work with businesses and partners to develop Business Continuity Plans and provide to the EOC for exercising review. | 2 | Business Resiliency Action Plan County COOP Plan
|  | ES3.8 | Emergency Management | Work with the identified local critical facility businesses to determine resources needed to aid in timely recovery efforts such as generators, mitigation projects, etc. | 2
|  | ES3.9 | Florida Department of Children Services School Districts Childcare Centers | Hold a workshop with day cares and school districts to determine a feasible approach to share resources for care for children under the age of 12 after a disaster. | 3
|  | ES3.10 | Incubator Facilities | Add "Business Continuity" to programs at incubator facilities. | 3
|  | ES3.11 | Florida Department of Children Services School Districts Childcare Centers | If deemed feasible, develop a plan to provide child care services when schools are closed for longer than a week. | 4
|  | ES3.12 | Chambers of Commerce | Reassess efforts and update plans and programs to fill identified gaps. | 5
|  | ES3.13 | Chambers of Commerce | Consider implementing a long-term recovery plan for businesses to retain employees as soon as possible following a storm event. | 5
Economic & Society | ES4: Increase skilled labor force. | ES4.1 | Workforce Agencies Community Colleges School Districts Economic Development Commissions | Collaborate with workforce and educational stakeholders to create a working group to facilitate the sustainable training of high school and tech school students in skilled labor. | 1
|  | ES4.2 | Workforce Agencies Community Colleges School Districts Economic Development Commissions | Implement/expand apprenticeship programs in high schools with partner businesses. | 2
|  | ES4.3 | ECFRPC Economic Development Commission Chambers of Commerce | Assess economic development plans, CRA plans, etc. for diversification and identify adaptative measures to economic vulnerabilities. | 2
|  | ES4.4 | ECFRPC Economic Development Commission Chambers of Commerce | Create/update and disseminate an educational infographic for businesses with emergency information to access for post disaster needs. | 2 | Business Continuity of Operations Plan County COOP Plan
|  | ES4.5 | Workforce Agencies School Districts Higher Education/Tech Schools Community Colleges Economic Development Commissions | Work with local colleges and tech schools to create programs to cross train manufacturing and installation sectors to create streamlined, sustainable job sectors with new titles. | 3
|  | ES4.6 | Workforce Agencies School Districts Higher Education/Tech Schools Community Colleges Economic Development Commissions | Develop baseline data and benchmarks to assess success of approach and growth in skilled labor force. | 3
|  | ES4.7 | Workforce Agencies School Districts Community Colleges Higher Education/Tech Schools Economic Development Commissions | Reassess efforts and update plans and programs to fill identified gaps. | 4
|  | ES4.8 | Workforce Agencies School Districts community Colleges Higher Education/Tech Schools Economic Development Commissions | Implement/increase activities to fill gaps identified in task ES4.7. | 5
|  | ES4.9 | Workforce Agencies School Districts Economic Development Commissions | Add "makerspace" facilities based on identified needs. | 5
Economic & Society | ES5: Improve social equity and justice in decision making process. | ES5.1 | All Jurisdictions | Host community meetings in underserved, low income communities to discuss projects within and just outside the community. | on-going
|  | ES5.2 | All Jurisdictions | Partner with local organizations and faith-based organizations to provide feedback concerning needs and opportunities specific to a project or program. | on-going
|  | ES5.3 | All Jurisdictions | Conduct health impact assessments when considering projects that may affect underserved, low income communities, and determine benchmark health outcomes. | on-going
|  | ES5.4 | Emergency Management All Jurisdictions | Host specific community meetings in underserved, low income communities to discuss resilience and disaster response. | 1
|  | ES5.5 | Planning Departments UF IFAS Extension Communications Departments | Engage with communities to identify gaps and priorities in the decision making process to improve social equity and justice. | 1
|  | ES5.6 | Economic Development Chambers of Commerce Small Businesses | Connect communities with non-profit and faith based organizations to address post-disaster issues such as the ability to return to the workforce after hazard events. | 2
|  | ES5.7 | Planning Departments Communications Departments UF IFAS Extension | Create an outreach plan to involve all communities in an engaging opportunity to be a part of local decisions. Utilize priorities and findings from ES5.5. | 3
|  | ES5.8 | Economic Development Chambers of Commerce Small Businesses UF IFAS Extension | Work with employers and employees to implement findings, processes, etc. determined from ES5.5. | 3
|  | ES5.9 | Planning Departments Communications Departments | Implement the outreach plan. | 4
|  | ES5.10 | Communications Department | Reassess the gaps that remain in community involvement outcomes. | 5

## Infrastructure and Environment
Goal | Objective | Action | Agency | Task | Year | Related Plans
Infrastructure and Environment | IE1: Prioritize the use of Green Infrastructure as a first line of defense. | IE1.1 | Public Works Department Natural Resource Department Environmental Department SJRWMD FDEP | Conduct an audit of coastal areas to identify locations for living shorelines and prioritize areas for implementation. (Example: UCF Study in Brevard, Gulf of Mexico Alliance Living Shoreline Study for Tampa Bay Region) | 1
|  | IE1.2 | Transportation Department Engineering Department Public Works Department TPO FDOT | Include narrative to include use of green infrastructure to create "green streets" to mitigate stormwater impacts where feasible in project prioritization and programming. | 1 | Long Range Transportation Plan TPO Priority Project Listing
|  | IE1.3 | Public Works Department Natural Resource Department SJRWMD FDEP Florida Sea Grant | Create/implement/expand a program or partnership to educate property owners about the benefits of living shorelines and assist with installation. | 2
|  | IE1.4 | Planning Department Sustainability Board | Conduct an audit to improve urban tree canopy cover in jurisdiction and develop an Urban Canopy Plan. | 2 | Sustainability Plan
|  | IE1.5 | Planning Department Natural Resource Department Environmental Department | Assess comprehensive plan, LDRs and process applications for barriers to implementing green infrastructure and to prioritize natural solutions versus engineered engineering projects. | 2 | Comprehensive Plan Land Development Regulations
|  | IE1.6 | FDEP SJRWMD Natural Resource Department Environmental Department NEE | Develop a Restoration Plan(s) to prioritize the restoration of tidal wetlands, dunes and salt marshes and create living shorelines to soften the impacts of wave-induced erosion in high risk areas. Include indicators to measure success and return on investment. | 3 | Restoration Paln
|  | IE1.7 | Planning Department Sustainability Board | Prioritize areas to improve urban tree canopy and develop action plan for implementation. | 3 | Sustainability Plan
|  | IE1.8 | Planning Department Natural Resource Department Environmental Department | Update comprehensive plans, LDRs and process to address barriers to implementing green infrastructure and make it a priority to assess natural solutions as a first step prior to engineering solutions based on findings in IE1.5. | 3 | Comprehensive Plan Land Development Regulations
|  | IE1.9 | Planning Department Natural Resource Department Environmental Department | Develop incentives for residents, businesses, and developers to use living shorelines and other green infrastructure techniques as a priority. | 4
|  | IE1.10 | Natural Resource Department Environmental Department | Create partnerships with colleges, NGOs, contractors and others to install and maintain green infrastructure. | 4
|  | IE1.11 | Planning Department Natural Resource Department Environmental Department | Analyze funding sources to move projects and programs forward that focus on Green Infrastructure. (ex: Brevard Living Shoreline Program) | 5
|  | IE1.12 | Planning Department Natural Resource Department Environmental Department | Conduct assessment on green infrastructure projects based on indicators established in the plan to measure success and ROI. | 5
|  | IE1.13 | Planning Department Natural Resource Department Environmental Department | Reassess plans, procedures, programs and policies to improve on any lessons learned. | 5 | Comprehensive Plan Land Development Regulations Sustainability Plan Restoration Plan
Infrastructure & Environment | IE2: Promote interconnectivity of natural lands for habitat migration. | IE2.1 | SJRWMD Natural Lands Program Natural Resource Department FFWCC FDEP 1000 Friends of Florida | Work continuously with advocacy groups to inform the public on development strategies that support biodiversity and interconnectivity. | on-going
|  | IE2.2 | SJRWMD Natural Lands Program Natural Resource Department FFWCC FDEP USACE 1000 Friends of Florida | Assess coastal nesting areas based on future conditions to develop preservation strategies viability of these areas. | 1
|  | IE2.3 | Natural Lands Program ECFRPC SJRWMD FFWCC FDACS USDA Natural Resource Department FDEP 1000 Friends of Florida | Assess undeveloped lands, agricultural lands, natural lands and migrating habitats to determine future priority corridors and properties for acquisition based on future conditions. Utilize the SLAMM model or other models as appropriate. | 1
|  | IE2.4 | SJRWMD Natural Lands Program Natural Resource Department FFWCC FDEP USACE 1000 Friends of Florida | Further develop preservation strategies for coastal nests (birds, turtles, etc.) to ensure the ecological and economic viability of the coastline and incorporate into related plans. | 2
|  | IE2.5 | Natural Lands Program ECFRPC SJRWMD FFWCC FDACS USDA Natural Resource Department FDEP 1000 Friends of Florida | Conduct a regional exercise with stakeholders to discuss the findings of IE2.3 and work to establish a regional plan to protect the priority corridors. | 3 | Conservation and Acquisition Plan Regional Natural Lands Corridor Plan
|  | IE2.6 | Local Government Commission Jurisdictional Departments Public FFWC FWS | Conduct survey of stakeholders to assess priority and funding of conservation lands for acquisition and maintenance. | 3
|  | IE2.7 | Natural Resource Department FDEP SJRWMD FWC FWS | Re-evaluate and update conservation and acquisition plans to implement findings from future corridor assessment and prioritization plan. | 4 | Conservation and Acquisition Plan
|  | IE2.8 | Planning Departments | Update comprehensive plan and other plans/codes with appropriate language to prevent future development from infringing on these priority corridors. | 4 | Comprehensive Plan Land Development Regulations
|  | IE2.9 | SJRWMD Natural Lands Program Natural Resource Department FDEP 1000 Friends of Florida NGOs FFWCC | Evaluate strategies and alternative analysis for longer term funding for acquisition / management program. | 5
Infrastructure & Environment | IE3: Enhance stormwater systems to be more resilient. | IE3.1 | Planning Department Public Works Department Natural Resources Stormwater Management | Consider stormwater master plan designs that utilizes an interconnected system of green infrastructure to reduce stormwater impacts. | on-going | Stormwater Master Plan Mobility Master Plan
|  | IE3.2 | Public Works Department All Local Government Commission ECFRPC | Procure funding and staff/contractor to update all stormwater system facilities in a master GIS database. | 1
|  | IE3.3 | Transportation Department Engineering Department Public Works Department TPO FDOT | Consider future inundation and nuisance flooding to determine areas of flood impacts to roadway stormwater infrastructure. | 1 | Long Range Transportation Plan TPO Priority Listing
|  | IE3.4 | Public Works Department Environmental Department Natural Resource Department | Evaluate existing green space for stormwater retention and evaluate findings based on future conditions. | 1
|  | IE3.5 | Public Works Department Stormwater Management Department | Develop strategies to prioritize and implement the use of green space in stormwater management. | 2
|  | IE3.6 | Public Works Department Stormwater Management Department | Assess stormwater system facilities to vulnerabilities to future inundation and erosion including elevations of outfalls into surface water bodies. | 2 | Stormwater Master Plan Vulnerability Analysis Studies
|  | IE3.7 | Public Works Department Stormwater Management Department | Prioritize areas of critical vulnerable stormwater infrastructure. Review other projects to determine if improvement projects can be addressed simultaneously for a greater cost benefit. | 3 | Stormwater Master Plan
|  | IE3.8 | Public Works Department Environmental Department Natural Resource Department Stormwater Management Department | Prioritize areas for green space to be utilized in design for stormwater management. | 3
|  | IE3.9 | Planning Department Public Works Department Stormwater Department | Develop prioritization process and funding mechanisms for infrastructure projects in Adaptation Action Areas. Incorporate into Stormwater master plan. | 3 | Stormwater Master Plan
|  | IE3.10 | Public Works Department Stormwater Management Department | Identify feasible improvements, mitigation or adaptation strategies to address vulnerable stormwater system areas. Update stormwater master plan for implementation and add to Capital Improvement Plan; other project plans; or seek funding to implement the projects. | 4 | Stormwater Master Plan
|  | IE3.11 | Planning Department Public Works Department Stormwater Department | Conduct a risk-based cost-benefit analysis for mitigation strategies of stormwater infrastructure identified as part of the natural hazard vulnerability assessment. | 4
|  | IE3.12 | Planning Department Public Works Department Stormwater Department | Update stormwater master plan with updated project list based on cost-benefit analysis. | 5
|  | IE3.13 | Public Works Department Stormwater Management Department | Reassess outfall and infrastructure elevation data to determine any gaps in data collection and analysis. | 5
|  | IE3.14 | Planning Department Public Works Department Transportation Engineering Departments FDOT TPO | Identify a process or mechanism to determine what infrastructure/areas may not be upgraded or mitigated at a certain time or impact. Reference previous data/information developed on stormwater and cost/benefit analysis in this analysis in order to help create a legal justification of decisions. | 5 | All previous vulnerability analysis, master plans and cost benefit studies.
Infrastructure and Environment | IE4: Improve water quality in surface water bodies. | IE4.1 | Indian River Lagoon Council All Local Jurisdiction Commission FDEP SJRWMD | Continue financial/staff support of programs and projects to improve water quality. | on-going
|  | IE4.2 | Indian River Lagoon Council FDEP SJRWMD UF IFAS Extension Public Works Department | Identify and educate communities about best management practices (BMP's) for reducing nutrient loads flowing into surface waters via residential, commercial, industrial and agricultural lands. | on-going
|  | IE4.3 | FDACS USDA UF IFAS Extension | Educate agriculture land owners on fertilizer best practices as well as the ecological resources their property provides in regards to resilience and mitigation. | on-going
|  | IE4.4 | FDEP SJRWMD Colleges/Universities ECFRPC | Identify projects and programs aimed at improving water quality and conduct a gaps analysis. | 1
|  | IE4.5 | FDEP SJRWMD Indian River Lagoon Council | Review current total maximum daily load (TMDL) requirements and recommend new targets. | 2
|  | IE4.6 | Marine Resource Council ECFRPC UF IFAS Extension | Evaluate existing fertilizer ordinances and successfulness. Conduct gap analysis to determine a regional approach. | 2
|  | IE4.7 | FDEP SJRWMD Colleges/Universities ECFRPC | Evaluate policies or ordinances for enhancing septic tank standards along waterways. | 2
|  | IE4.8 | Planning Department All Local Jurisdiction Commission | Develop and adopt a fertilizer ordinance. | 2
|  | IE4.9 | FDACS USDA UF IFAS Extension | Re-assess/prioritize areas of agricultural run-off. | 2
|  | IE4.10 | FDACS USDA UF IFAS Extension | Evaluate existing outreach programs and enhance where necessary to work with property owners to reduce runoff in agriculture priority areas from ES4.9. | 3
|  | IE4.11 | FDOT TPOs | Assess procedures and requirements for design alternatives to promote resilience of natural lands and waterway health. | 3
|  | IE4.12 | Marine Resource Council ECFRPC | Develop and implement steps to promote the adoption of fertilizer ordinances region wide in areas where they do not exist. | 4
|  | IE4.13 | Indian River Lagoon Council FDEP Marine Resource Council Public Works Department Planning Department SJRWMD FDACS Public Works Department | Reassess success of programs and policies aimed to improve water quality in surface water bodies. | 5
|  | IE4.14 | Indian River Lagoon Council FDEP SJRWMD Public Works Department | Investigate financial strategies to continue programs into the future. | 5
Infrastructure & Environment | IE5: Incorporate resiliency into local and regional plans, policies, processes and objectives | IE5.1 | NASA Port Canaveral Patrick Air Force Base All Jurisdictions FDOT TPOs | Utilizing input gathered from the RRAP Sea Level Rise Steering Committee, update policies, plans and procedures with the RRAP recommendation for planning for sea level rise and for use in the geographic delineation of an "Adaptation Action Area" where appropriate. | 1 | Comprehensive Plan Land Development Regulations Long Range Transportation Plan TPO Priority Project Methodology Local Mitigation Strategy Others
|  | IE5.2 | Planning Department | Determine if Adaptation Action Area designation and policies are appropriate for the jurisdiction. If determined appropriate, develop policies and maps to identify the area, purpose and other related policies. | 1 | Comprehensive Plan
|  | IE5.3 | All Jurisdictions | Create cross-discipline review committees to assist in the audit of various plan goals policies and strategies as they relate to resilience and review impacts of new projects and developments in regards to resilience. | 1 | All plans
|  | IE5.4 | All Local Jurisdiction Commission All Jurisdictions | Adopt an "Adaptation Action Area" that includes the 100-year floodplain, the adopted sea level rise hazard zone, and the Coastal High Hazard Zone (Category 1 Storm Surge). | 2 | Comprehensive Plan Land Development Regulations
|  | IE5.5 | Planning Department | Assess other plans to reference Adaptation Action Areas and incorporate language as appropriate. | 2
|  | IE5.6 | Planning Department Sustainability Board | Audit Comprehensive Plan to ensure that resiliency strategies are adequately addressed and policies are compatible in all applicable sections. Add/adjust appropriate language where needed. | 2 | Comprehensive Plan
|  | IE5.7 | Planning Department Sustainability Board Emergency Management Public Works | Audit Comprehensive plan against other plans (i.e. CRA plans, Downtown Development Plans, Economic Development Plans, LDRs, PDRP) to ensure compatibility of addressing resiliency and future development based on future conditions. | 2 | Comprehensive Plan CRA plan Downtown Development Plans Economic Development Plans Sustainability Plans Stormwater Plans Post Disaster Redevelopment Plans
|  | IE5.8 | Planning Department Sustainability Board ECFRPC | Develop a Sustainability and/or Resiliency Plan if deemed appropriate by stakeholders and previous efforts. | 2 | Sustainability Plan Resilience Plan
|  | IE5.9 | Planning Department Sustainability Board ECFRPC UF IFAS Extension FDEP SJRWMD | Adopt changes in all necessary plans to reduce the volume of nutrient loads and fertilizers from public and private property flowing into the Indian River Lagoon utilizing the research developed by FDEP and the SJRWMD derived from action IE4.4. | 2 | Land Development Regulations Comprehensive Plan
|  | IE5.10 | Emergency Management LMS Working Group ECFRPC | Update the County FMP/LMS to include the future vulnerability analysis of public facilities. | 2
|  | IE5.11 | Emergency Management LMS Working Group | Update mitigation prioritization process to include Adaptation Action Area proximity, future conditions and other criteria identified by the LMS Working Group. | 2
|  | IE5.12 | FDOT TPO | Implement the requirement that alternative analysis of future conditions and consideration for long-term resilience and health of natural systems be included in planning and engineering of projects. | 3
|  | IE5.13 | Planning Department Sustainability Board ECFRPC | Add and adopt policies to Comprehensive Plan, and other plans, that result from the recommendations identified in the Resiliency/Sustainability Plan and comp plan audit. | 3 | Comprehensive Plan Other Plans as appropriate
|  | IE5.14 | Public Works Department | Update stormwater master plan to include future flooding and inundation findings; priorities and projects where possible. | 3 | Stormwater Master Plan
|  | IE5.15 | Planning Department Sustainability Board ECFRPC | Update/Enhance/Develop Design Guidelines within Land Development Regulations that protect and buffer structures from the impact of hazards. These guidelines should address sea level rise, storm surge, flooding, wind damage, and the urban heat island effect. | 3 | Land Development Regulations Sustainability Plan
|  | IE5.16 | Planning Department Sustainability Board ECFRPC | Enhance/Develop an energy code to encourage property owners and government facilities to reduce carbon emissions and mitigate the urban heat island effect. | 3 | Land Development Regulations Sustainability Plan
|  | IE5.17 | Planning Department Sustainability Board ECFRPC | Create Florida Green Building Codes or LEED-accreditation benchmarks for new and existing buildings, including public facilities, within the Land Development Code and Energy Code. | 3 | Land Development Regulations Sustainability Plan
|  | IE5.18 | Planning Department Sustainability Board ECFRPC | Update Land Development Regulations and the Comprehensive Plan to set new parking and stormwater standards, utilizing the information derived from LS3.2. | 3 | Comprehensive Plan Land Development Regulations
|  | IE5.19 | Planning Department Sustainability Board ECFRPC | Establish policies and practices for area-wide metrics such as net density requirements that cluster development away from high hazard areas. | 4 | Comprehensive Plan Land Development Regulations
|  | IE5.20 | Planning Department Sustainability Board ECFRPC | Update Land Development Regulations to alter coastal setback codes utilizing the information obtained from vulnerability analysis and task IE1.9 and IE2.4. | 4 | Land Development Regulations
|  | IE5.21 | Public Works Department Planning Department ECFRPC | Update CIP to implement priority projects identified through vulnerability analysis and appropriate mitigation projects. | 5 | Comprehensive Plan
Infrastructure and Environment | IE6: Preserve and adapt the built environment to keep people safe from and mitigate current and future natural hazards. | IE6.1 | Planning Department Public Works Department Natural Resource Department Emergency Management | Conduct assessment to determine vulnerabilities to sea level rise, storm surge, coastal erosion and flooding for the built environment, natural resources and undeveloped properties. | 2 | Vulnerability Assessment
|  | IE6.2 | Planning Department Public Works Department LMS Working Group TPO | Create (or add where one exists) a checklist for the planning, prioritization and funding of green and gray infrastructure projects to include assessment of vulnerabilities and if/how the project addresses long-term resiliency. | 3
|  | IE6.3 | Planning Department; Building Department; Public Works | Assess community owned vulnerable or damaged coastal properties and determine best long term approach for each property. | 2
|  | IE6.4 | Planning Department Public Works Department LMS Working Group TPO | Prioritize public infrastructure within Adaptation Action Areas for adaptation/mitigation strategies to the effects of high winds, storm surge, flooding and wave velocity. | 2
|  | IE6.6 | Planning Department Building Department | Review best practices for updating coastal setback and building rebuild codes that mitigate the potential effects of coastal erosion. | 2
|  | IE6.7 | Planning Department | Develop incentives for developers to build outside vulnerable areas or build in a resilient/sustainable way in vulnerable areas. | 2
|  | IE6.8 | Planning Department | Develop policies and strategies to reduce heat island effects through new projects, redevelopment and other opportunities. | 2
|  | IE6.9 | Planning Department Building Department | Develop incentives to developers that use methods consistent with Low Impact Development (LID) standards, Florida Green Building Coalition, and techniques to reduce the heat island effect. | 2 | LDRs Comprehensive Plan
|  | IE6.10 | All Local Jurisdiction Commission Emergency Management | Provide dedicated funding for annual tree maintenance near power lines to help prevent storm damage and allow access for electricity providers to fix broken power lines in an efficient manner following a natural disaster. | 2 | County COOP Plan City COOP Plan Debris Management Plan
|  | IE6.11 | Planning Department Public Works Department LMS Working Group TPO | Review other projects to determine if improvement projects can be addressed simultaneously for a greater cost benefit. | 3
|  | IE6.12 | Planning Department | Research potential strategies addressing undeveloped parcels located within the Adaptation Action Area. | 3
|  | IE6.13 | FDEP SJRWMD Public Works Department | Develop a risk assessment to determine wellfields, groundwater and underground infrastructure at risk to saltwater intrusion. | 3 | Groundwater Asset Risk Analysis
|  | IE6.14 | Planning Department Public Works Department LMS Working Group TPO | Develop possible mitigation strategies of at-risk public infrastructure identified as part of the natural hazard vulnerability assessment. | 3
|  | IE6.15 | Planning Department Public Works Department TPO | Develop prioritization process and funding mechanisms for infrastructure projects in Adaptation Action Areas. Incorporate into CIP, stormwater master plan, long range transportation plan, and other appropriate plans and procedures. | 4 | Comprehensive Plan Stormwater Master Plan LRTP
|  | IE6.16 | Planning Department Public Works Department LMS Working Group TPO | Conduct a risk-based cost-benefit analysis for mitigation strategies of at-risk public infrastructure identified as part of the natural hazard vulnerability assessment. | 4
|  | IE6.17 | Planning Department | Implement incentives to developers to build outside of vulnerable areas. | 4
|  | IE6.18 | Planning Department Building Department | Implement incentives to developers that use methods consistent with Low Impact Development (LID) standards and Florida Green Building Coalition. | 4
|  | IE6.19 | FDOT TPO | Conduct a vulnerability analysis for all vulnerable causeways and bridges identified in the 2017 Sea Level Rise Vulnerability Analysis using high resolution LIDAR data. Prioritize improvements based on the results of this assessment. | 4 | Long Range Transportation Plan TPO SLR Vulnerability Analysis Causeway Vulnerability Assessment
|  | IE6.20 | FDOT TPO Colleges & Universities | Create a research committee consisting of FDOT, the TPO and a academia and environmental experts to develop standards for causeway designs that use innovative techniques to limit the impacts of sea level rise, flooding and storm surge and improve water quality and natural resource resilience. | 4 | Causeway Vulnerability Assessment
|  | IE6.21 | Planning Department Public Works Department LMS Working Group TPO Emergency Management | Evaluate success of implemented actions and gaps to be addressed. | 5
Infrastructure & Environment | IE7: Improve community mobility while improving vulnerable transportation infrastructure | IE7.1 | Emergency Management Transit Agencies | Update evacuation plans to represent newest data of areas that are transportation dependent that will need assistance in evacuation and re-entry. | 1
|  | IE7.2 | ECFRPC FDOT TPOs | Host a workshop focused on green infrastructure and multi-modal transportation highlighting tools and concepts to accomplish it. | 2
|  | IE7.3 | FDOT TPO Planning Department Public Works Department | Prioritize and implement mitigation efforts on trails within the Adaptation Action Area and other vulnerable areas. | 3 | LRTP
|  | IE7.4 | TPO Planning Department Public Works Department | Identify areas where bicycle and pedestrian improvements can be included in transportation projects that mitigate roadways vulnerable to natural hazards (green streets). Utilize Safe Routes to School. | 4
|  | IE7.5 | Emergency Management Transit Agencies ECFRPC FDOT TPO Planning Department Public Works Department | Evaluate success of implemented actions and gaps to be addressed. | 5